## Sheet1
Defect ID | Description | Severity | Priority | Module | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To
DEF001 | Payment fails for international transactions | Critical | High | Payments | Log in > Add international bank account > Initiate payment > Submit | Payment completes successfully | Payment fails with an unknown error | Open | Backend Team
DEF002 | OTP not received during login | Critical | High | Authentication | Log in with a registered account > Wait for OTP | OTP is sent to the registered number | OTP is not received | Open | Backend Team
DEF003 | Account locked after valid OTP verification | Critical | High | Authentication | Log in > Enter valid OTP > Submit | User redirected to dashboard | Account gets locked unexpectedly | Open | Security Team
DEF004 | Application crashes on adding a payment method | High | High | Payments | Log in > Go to payment methods > Add > Submit | Payment method is added | Application crashes | Open | Frontend Team
DEF005 | Transaction history not loading for large records | High | Medium | History | Log in > Navigate to transaction history | Transaction history is displayed | Page keeps loading indefinitely | Open | Backend Team
DEF006 | Password reset email not sent | High | Medium | Authentication | Go to Forgot Password > Enter email > Submit | Password reset email is sent | No email received | Open | Backend Team
DEF007 | Negative values accepted in payment field | Medium | High | Payments | Log in > Initiate payment > Enter negative amount > Submit | Validation error is displayed | Payment initiated with negative amount | Open | Frontend Team
DEF008 | Incorrect error for invalid UPI ID | Medium | Medium | Payments | Log in > Add invalid UPI ID > Submit | 'Invalid UPI ID' error displayed | Generic error shown | Open | Backend Team
DEF009 | Slow response time during peak hours | High | High | Performance | Log in during peak hours > Perform transaction | System responds within 3s | Takes 10+ seconds | Open | Performance Team
DEF010 | UI misalignment on iPhone 13 | Low | Low | UI/UX | Open on iPhone 13 > Navigate pages | UI is aligned | Buttons overlap | Open | UI Team